## format it properly , the sprint
No. | Epic | Feature | Stories | Subtasks | Story Points | Sprint
1 | Create a web-based platform to educate and engage users about the Agile Manifesto and methodologies | 1. Homepage for Agile Manifesto | •⁠ ⁠Story 1.1: Design and implement a visually appealing homepage. •⁠ ⁠Story 1.2: Add an introduction to Agile and its history. •⁠ ⁠Story 1.3: Include navigation to other sections of the platform. | 1.1.1 Create wireframes for the homepage 1.1.2 Develop HTML and CSS for the layout 1.1.3 Integrate animations using JavaScript 1.1.4 Conduct user testing and gather feedback | 5 | Sprint 1
[5 empty] | 3 | Sprint 1
[5 empty] | 2 | Sprint 1
2 |  | 2. Agile Values and Principles | ⁠ ⁠Story 2.1: Create a page to display the four core Agile values. •⁠ ⁠Story 2.2: Implement an interactive feature to explain the 12 principles. •⁠ ⁠Story 2.3: Add examples to illustrate each value and principle. |  | 3 | Sprint 2
[5 empty] | 8 | Sprint 2
[5 empty] | 5 | Sprint 2
3 |  | 3. Resource Library | ⁠Story 3.1: Design a library for Agile practices (Scrum, Kanban, etc.). Story 3.2: Include downloadable resources like templates and guides. Story 3.3: Add search and filter functionality. |  | 5 | Sprint 3
[5 empty] | 3 | Sprint 3
[5 empty] | 5 | Sprint 3
4 |  | 4. Collaboration Features | Story 4.1: Develop a discussion forum for users. Story 4.2: Enable users to comment on resources and principles. Story 4.3: Implement user authentication for collaboration features. | 4.1.1 Design the comment input field and UI 4.1.2 Develop backend APIs for storing comments 4.1.3 Implement frontend integration with APIs 4.1.4 Test the comment functionality | 5 | Sprint 4
[5 empty] | 8 | Sprint 4
[5 empty] | 5 | Sprint 4